## Sprint#0
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Business Requirement Document | 27 | 9 | 6 | 5 | 3 | 3 | 1 | 0 | 0
Management Plan | 17 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 2
Create Database | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 1
Populate Sprint Board | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Estimated Remaining Effort | 54 | 47.25 | 40.5 | 33.75 | 27 | 20.25 | 13.5 | 6.75 | 0
Actual Remaining Effort | 54 | 45 | 39 | 33 | 29 | 26 | 10 | 3 | 0
https://reqtest.com/agile-blog/burndown-chart-tool/

## Sprint#1
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Product Requirements Document | 16 | 4 | 2 | 3 | 1 | 3 | 2 | 1 | 0
Update BRD | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Update Management Plan | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
Start Architectural and Design Documents | 19 | 0 | 0 | 3 | 2 | 4 | 2 | 3 | 5
Estimated Remaining Effort | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Actual Remaining Effort | 40 | 36 | 34 | 27 | 23 | 15 | 11 | 6 | 0
Generate Graph for this

## Sprint#2
Tasks |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
User Manual | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Code Release 1.0 | 40 | 0 | 1 | 8 | 9 | 7 | 8 | 5 | 2
Team Evaluation of Code | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Estimated Remaining Effort | 51 | 44.625 | 38.25 | 31.875 | 25.5 | 19.125 | 12.75 | 6.375 | 0
Actual Remaining Effort | 90 | 85 | 84 | 76 | 67 | 60 | 50 | 43 | 39

## Sprint#3
Tasks |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Code Release 2.0 | 30 | 0 | 8 | 5 | 4 | 6 | 4 | 3 | 0
User Manual | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
User Eval on Code Release 2.0 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
Update Project Documentation | 16 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0
Estimated Remaining Effort | 54 | 47.25 | 40.5 | 33.75 | 27 | 20.25 | 13.5 | 6.75 | 0
Actual Remaining Effort | 90 | 90 | 82 | 77 | 69 | 59 | 49 | 36 | 36

## Sprint #4
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Team Sprint #4 Planning Meeting | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Update ADD | 8 | 0 | 3 | 1 | 2 | 0 | 1 | 1 | 0
Create Test Plan | 18 | 0 | 5 | 2 | 2 | 2 | 4 | 3 | 0
Create Machine Learning Model | 21 | 0 | 5 | 5 | 3 | 6 | 2 | 0 | 0
Database/Back-End Account Creation | 5 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0
Test Account Creation and Login | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Database/Back-end Profile | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI for Login to Website using Google Account | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0
Test Profile Editing | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI for Player Profile | 8 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 0
Estimated Remaining Effort | 77 | 67.375 | 57.75 | 48.125 | 38.5 | 28.875 | 19.25 | 9.625 | 0
Actual Remaining Effort | 77 | 74 | 56 | 46 | 37 | 26 | 14 | 8 | 8

## Sprint #5
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Team Sprint #5 Planning Meeting | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create UI for Rating System to Rate Other Players | 5 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0
Connect Rating System to Database | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test Rating System | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI for Player Profile (Interests, Location, etc.) | 8 | 0 | 0 | 3 | 2 | 2 | 1 | 5 | 0
Datbase Profile Editing | 6 | 0 | 0 | 2 | 1 | 3 | 0 | 0 | 0
Test Profile Editing | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Database for Creating Events | 10 | 0 | 3 | 4 | 3 | 0 | 0 | 0 | 0
UI for Create an Event | 7 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0
Testing Create Event | 5 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0
UI for Join an Event | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database for Joining Events | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing Join Event | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create/Modify ML Data Set | 7 | 0 | 0 | 0 | 0 | 5 | 3 | 5 | 0
Create/Modify a Model | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing Model Using DataSet | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimated Remaining Effort | 92 | 80.5 | 69 | 57.5 | 46 | 34.5 | 23 | 11.5 | 0
Actual Remaining Effort | 92 | 89 | 83 | 69 | 59 | 47 | 40 | 29 | 29

## Sprint #6
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Team Sprint #6 Planning Meeting | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a User Manuel | 5 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0
UI for join an event | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Database for joining an event | 6 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0
UI for Rating System to Rate other players | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Connect Rating System to database | 10 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
Test Rating System | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
Testing Join event | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
Create/modify ML data set | 7 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0
Create/modify a model | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Test model using data set | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Research how to implement the API | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
Estimated Remaining Effort | 74 | 64.75 | 55.5 | 46.25 | 37 | 27.75 | 18.5 | 9.25 | 0
Actual Remaining Effort | 74 | 67 | 58 | 49 | 38 | 24 | 19 | 15 | 15

## Sprint #7
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Create/modify a model | 10 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Test model using data set | 15 | 2 | 2 | 3 | 1 | 0 | 0 | 0 | 0
star rating - other user can rate other profile | 7 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 0
star rating - other user cant' rate their own profile | 8 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
profile interactions - other user view other profile | 20 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0
Estimated Remaining Effort | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5
Actual Remaining Effort | 60 | 53 | 48 | 36 | 27 | 21 | 16 | 16

## Sprint #8
Tasks | Estimated Effort | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
Test model using Dataset | 15 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Apply ML model in either Python/Node.js and show it on UI | 10 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0
Test from users perspective | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
List of Local park within certain range | 10 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0
Create Map Around User | 10 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0
Test all Functionality | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Star rating - own user can't rate their own profile | 8 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0
Star rating - own user can rate other profile | 7 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0
Create a map of the local area around school | 11 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0
Estimated Remaining Effort | 75 | 65.625 | 56.25 | 46.875 | 37.5 | 28.125 | 18.75 | 9.375
Actual Remaining Effort | 75 | 66 | 58 | 45 | 39 | 34 | 34 | 33