## Slide 1: Sprint #5 Presentation
Jamil Khan, Chaz Del Prato, Benjamin Seo, Christine Duong, Brandon Le, John Him

## Slide 2: Updates
Management Plan
  Gantt Chart
  Burndown Chart
  Project Tracking Matrix
  Team Code Velocity
  Sprint Retrospective

## Slide 3: Sprint Goals
Create UI for Rating System to Rate Other Players
Connect Rating System to Database
Test Rating System
UI for Player Profile (Interests, Location, etc.)
Database Profile Editing
Test Profile Editing
Database for Creating Events
UI for Create an Event
Testing Create Event

## Slide 4: Sprint Goals (continued)
UI for Join an Event
Database for Joining Events
Testing Join Event
Create/Modify ML Data Set
Create/Modify a Model
Testing Model Using DataSet

## Slide 5: User Stories for This Sprint
Management Team:
As a management team, we want to be constantly learning and improving our Machine Learning model within our application.

## Slide 6: User Stories for This Sprint
Player:
As a player, I would like to be able to rate other players, so that I can enjoy each players sportsmanship.
As a player, I want to be able to edit a profile that shows my age, skill level, and interested sports, so that I get notified when a related game is started.
As a player, I want to be able to create an event, so that I can start a pick-up game
As a player, I want to be able to join an event, so that I can join a pick-up game

## Slide 7: APIs and Servers
APIs
Machine Learning Kit on Firebase.
Google Sign In/Sign Up
Modules (Grid, Bootstrap, etc.)
Etc.
Servers
We using Firebase Hosting, so we are serverless at this point.

## Slide 8: APIs and Servers
External 3rd Party APIs:
Google Sign in/ Sign up
Data Extracted from 3rd Party APIs:
Account Sign in/Sign up Credentials

## Slide 9: Type of ORM, ODM Libraries or Drivers Used in the Connection of Database to Server
JSData
  JSData converts data from JavaScript Objects to formats used by MySQL, MongoDB, RethinkDB, Firebase, etc. and vice versa

## Slide 10: Features in Data Sample
How many features are there in a data sample?
  Type_Sport, Gender, Skill_Level, Last_Month_games, Last_3m_avg_games, Players_Rating
What is the source of the training data?
  A website called Kaggle:
    https://www.kaggle.com/shirantha/bank-marketing-data-a-decision-tree-approach
  Thinking about what features correlate to what we want to recommend.
Did the team plot the data correlation between features and the label? What business relationship between features and labels that you can tell?
  Since we do not have our datasets yet, we cannot plot them. However the correlations between the features and the label are similar enough that we are able to use them.

## Slide 11: Machine Learning Deployment
How do we plan to deploy the machine learning model?
  At the moment, we are planning on deploying our model as a Web API.
Alternative deployment architectures?
  REST API = Web API

## Slide 12: Gantt Chart

## Slide 13: Burndown Curve

## Slide 14: Project Planning Matrix

## Slide 15: Sprint Board (Start)

## Slide 16: Sprint Board (End)

## Slide 17: User Features
How many total user features?
  Create account and log in/out
  Create an event
  Create Profile
Other features in progress
  User rating system
  Edit Profile Page UI
  Ability to join an event

## Slide 18: Sprint Retrospective
Our goal was to:
Create UI for Rating System to Rate Other Players
Connect Rating System to Database
Test Rating System
UI for Player Profile (Interests, Location, etc.)
Database Profile Editing
Test Profile Editing
Database for Creating Events
UI for Create an Event
Testing Create Event

## Slide 19: Sprint Retrospective
Our goal was to:
UI for Join an Event
Database for Joining Events
Testing Join Event
Create/Modify ML Data Set
Create/Modify a Model
Testing Model Using DataSet

## Slide 20: Sprint Retrospective
Our team’s total velocity is :
5 hours x 3 weeks x 6 members = 90 hours (story points).
We were not able to meet our sprint goal.
Overplanned.
Misjudged time availability.
Busy with other work.
A lot of problems came up when dealing with module compatibility.

## Slide 21: Sprint Retrospective
What we did not finish:
Create UI for Rating System to Rate Other Players
Connect Rating System to Database
Test Rating System
UI for Player Profile (Interests, Location, etc.) - Page Layout

## Slide 22: Sprint Retrospective
What we did not finished:
UI for Join an Event
Database for Joining Events
Testing Join Event
Create/Modify ML Data Set
Create/Modify a Model
Testing Model Using DataSet

## Slide 23: Sprint Retrospective
Current hours worked:
24 hours completed on finished tasks.
45 + hours currently worked overall for both unfinished and finished tasks.
Burndown Chart Analysis:
We were not able to meet our sprint goals due to availability and overestimating the tasks that we had planned this sprint. We ended up spreading ourselves thin and made all around progress but unable to accomplish many goals we had for the sprint.

## Slide 24: Sprint Retrospective
Team velocity for next sprint:
Keep the same team velocity to 90 hours.
Complete everything we were working on in sprint #5
No new tasks for next sprint.

## Slide 25: Code Evaluation
User Stories Implemented
For Sprint #5, we implemented:
  Users can login with google or their own account.
  Users can sign up with google or on their own email.
  User can logout.
  Users can create an event for a pick-up game
  User can Create and Edit Profile (no UI for Profile Page; Backend)
Code Function
Create account with google or their own email.
Sign in with google or their own account.
Logout.
Create event.

## Slide 26: Code Evaluation
Code Function
Create account with google or their own email.
Sign in with google or their own account.
Logout.
Create event.
Create/Edit Profile (no Profile Page; Backend)

## Slide 27: Code Evaluation
Platform
Web Application for all devices that is connected to the Internet
User Manual
Not implemented in the current build.
Number of Clicks/Entries per User Benefits
1-5 Clicks

## Slide 28: Code Evaluation
-Ities Requirement
Trying to implement:
  Scalability.
  Accessibility.
  Maintainability.
  Amiability.
  etc.

## Slide 29: Code Review
Updated account creation to actually save to the database.
https://pick-up-sportz-89c6e.firebaseapp.com/